{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["报价函","Sheet2","Sheet3"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"报价函","index":0,"n_rows":26,"n_cols":12,"rows_kept":26,"merged":[[0,0,0,7],[1,0,1,7],[3,7,6,7],[7,1,7,5],[8,0,8,7],[9,4,9,5],[9,6,9,7],[10,4,10,5],[10,6,10,7],[11,0,11,7],[12,5,12,6],[13,5,13,6],[14,5,14,6],[15,1,15,4],[15,5,15,6],[16,1,16,7],[17,0,17,7],[18,0,18,6],[19,0,19,7],[20,0,20,6],[21,0,21,7],[22,0,22,7],[23,0,23,7],[24,0,24,7],[25,0,25,7]],"flags":["formulas_cached_only"]}
["附件3：娄底职院医养大楼建设工程基坑监控观测服务费--投标报价函"]
["                          一、基坑监测费用"]
["序号","监测项目","测点布置    位  置","点（孔、条）数","观测 次数","单价报价（元）","单项总价报价（元）","备注"]
[1,"监测基准点",null,3,2,null,null,"服务期限预估180天"]
[2,"基坑水平位移","支护结构顶点",13,30]
[3,"基坑垂直位移","支护结构顶点",13,30]
[4,"周边建筑物沉降","周围建筑物",8,30]
[null,"合计：           "]
["二、房屋主体沉降观测费用\n"]
["序号","监测楼栋","测点布置位置","单价报价（元）","单项总价报价（元）",null,"备注"]
[1,"医养大楼","特征部位",{"$nulls":3},"服务期限预估540天"]
["                          三、材料费用"]
["序号","名称","测点布置位置","点（孔）数","单价（元）","单项成本总额（元）"]
[1,"直角棱镜","支护结构顶点",13]
[2,"L型沉降观测钉","周围建筑物",8]
[null,"合计：           "]
[null,"    以上三项总计金额:"]
["备注：  单价、总价报价都以整数报价且不能超过采购预算价"]
["1.以上预算按《工程勘察设计收费标准》（2002年修订版本）计算。"]
["2.根据设计图纸要求，确定本次监测项目及测点个数。",{"$nulls":10}," "]
["3.房屋主体监测周期主体整体趋于稳定，符合验收标准。"]
["4.项目监测周期按6个月预估，当基坑开挖深度≤H/3时，监测频率为3天一次；当基"]
["坑开挖深度为H/3～2H/3时，监测频率为2天一次；当基坑开挖深度为2H/3～H时，"]
["监测频率为每天一次；底板浇筑完成后7天内每二天监测一次，底板浇筑7～14天内"]
["每3天监测一次，底板浇筑14～28天内每七天监测一次，之后逐步放宽监测频率，"]
["若工期超过6个月，按以上单价进行签证收费。"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}